## RevisionReviewOutcome_History
Revision History
Date | Version | Author | Description of Change
2017-05-05 | DRAFT 1.0 | Kiệt Huỳnh | Initial draft
20/5/2017 | Final 1.0 | Kiệt Huỳnh | Thêm yêu cầu cần change
2018-06-21 | DRAFT 1.1 | Kiệt Huỳnh | Yêu cầu mới
Review and Outcome History
Date | Version | Reviewed by | Outcome
2017-05-05 | DRAFT 1.0 | DEV Team | Cần giảm business priority như đã thảo luận cho need 01 và need 02
20/5/2017 | Final 1.0 | Team Leader | Baselined, team dev, designer, security đã thống nhất thay đổi

## Needs
HỆ THỐNG PHẦN MỀM TỰ HỌC — YÊU CẦU CẢI TIẾN — V1.1
Need ID | Statement of Need | Business Area | Source of Need Statement | Business Priority | Status | Subject Area | Notes | Version
001 | Người dùng yêu cầu được đăng nhập thông qua Facebook | Phần mềm tự học online | Online Survey | Medium | Accepted | Chung |  | 1.0
002 | Hỗ trợ thêm xác thực 2 bước khi đăng nhập thông qua hệ thống | Phần mềm tự học online | Security Team | Medium | Accepted | Bảo mật |  | 1.0
003 | Tăng dung lượng được phép lưu trữ cho từng người dùng | Phần mềm tự học online | Online Survey | Medium | Accepted | Chức năng hệ thống |  | 1.0
004 | Thay đổi màu của button Đăng nhập | Phần mềm tự học online | User Request | Low | Accepted | Trải nghiệm người dùng |  | 1.0
005 | Tăng kết quả tìm kiếm được hiển thị trong một trang | Phần mềm tự học online | User Request | Low | Under Review | Trải nghiệm người dùng |  | 1.1
006 | Thêm tính năng đáng dấu nội dung ưu thích | Phần mềm tự học online | User Request | Medium | Proposed | Chức năng hệ thống |  | 1.1
007 | Thêm tính năng cho phép lưu nội dung học ra file PDF | Phần mềm tự học online | User Request | Medium | Proposed | Chức năng hệ thống |  | 1.1
008 | Chỉnh sửa màu trên thanh điều hướng để dễ đọc chữ hơn | Phần mềm tự học online | Online Survey | Low | Under Review | Trải nghiệm người dùng |  | 1.1
009 | Thêm bộ lọc theo rating khi tìm kiếm nội dung | Phần mềm tự học online | User Request | Low | Under Review | Chức năng hệ thống |  | 1.1
010 | Thêm tính năng follow người đăng nội dung | Phần mềm tự học online | User Request | Low | Proposed | Chức năng hệ thống |  | 1.1

## Requirements
HỆ THỐNG PHẦN MỀM TỰ HỌC — Requirements — v2.1
This Worksheet is Provided as an Example Only & is not meant to illustrate a complete set of requirements
Requirement | Requirement No. | Need(s) | Requirement Type | Addressed by | Implementa- tion Priority | Timeframe | Use Case(s) | Testability | Notes
Hệ thống phải sử dụng Facebook API và cung cấp thông tin cần thiết để có thể xác thực | REQ-001 | 001 | External Interface | User | 2 | 2017 - Q1 | N/A | Test Plan
Xây dựng lại chức năng xác thực cho người dùng. Sau khi đăng nhập sẽ gửi email để lấy mã xác thực | REQ-002 | 002 | Functional Requirement | User | 2 | 2017 - Q2 | N/A | Test Plan
Điều chỉnh lại cấu hình hiện tại của hệ thống để tăng dung lượng lưu trữ của từng người | REQ-003 | 003 | Business Rule | N/A | 1 | 2017 - Q1 | N/A | Test Plan
Chỉnh lại button đăng nhập thành màu xanh với mã #163780 | REQ-004 | 004 | Design Constraint | N/A | 3 | 2017 - Q1 | N/A | Test Plan

## Data
Business Areas | Business Priorities | Statuses | Subject Areas | Use Cases |  |  | Requirement Types |  | Addressed by | Implementation Priorities | Testability Methods
Name | Name | Name | Name | ID | Name | Primary Actor | Name | Notes | Name | Name | Name
Phần mềm tự học online | High | Proposed | Chức năng hệ thống | N/A | N/A | N/A | Business Requirement | A business requirement states a high-level business objective. It should answer the question: “Why are we devoting resources to this requirement?” Categories: • Financial benefits such as reduced costs, increased revenue, enhanced market share • Improvements in business operations • Strategic positioning or brand enhancement • Regulatory compliance | Dev Team | 1 | Test Plan
| Medium | Under Review | Trải nghiệm người dùng | UC-001 | UC-001 NAME | Public User or Admin User | Business Rule | A business rule is an organization policy, industry standard, or law or government regulation that defines, constrains, or governs some aspect of the business. Most business rules exist independently from a specific software system (that is, they are not software requirements), should be treated as an enterprise-level asset, and should be documented separately from system-specific requirements. A business rule can lead to various sets of functional requirements. Business rule sub-types include: • Action Enabler: describes an action to be taken when a condition is true, usually written as an “if-then” or “when-then” statement (for example, “If the customer has an active membership, then display membership rates”) • Business Constraint: a policy (whether determined by management or an external regulatory agency) that limits what the system or an actor within the system can do. • Computation, Calculation, or Formula: self-explanatory (for example, “The total price shall be calculated as …”). • Fact: a simple factual statement, often associated with data attributes (for example, “Each customer has a unique customer number”). • Inference: describes a change to the status of data, usually written as an “if-then” statement (for example, “If the customer does not pay for the reservation by the payment due date, then change the reservation status to canceled”). | User | 2 | Demonstration
| Low | Accepted | Dữ liệu | UC-002 | UC-002 NAME | Public User | Data Definition | Information that the system will Create, Read, Update, and/or Delete (CRUD). Typically this includes the name of a business object, its attributes, rules, and CRUD functions. | Vendor | 3 | Simulation
|  | Rejected | Phần cứng | UC-003 | UC-003 NAME | Admin User | Design Constraint | A limitation of the solution or of its implementation. Examples: • “Funding for this project is only $5,000.” • “The UI has to be compatible with the following web browsers: …” • “Coding must be in Java.” | Both | 99 | Inspection
|  |  | Chung | UC-004 | UC-004 NAME | Public User or Admin User | External Interface | An interface between the system and the outside world. There are four types of external interfaces: • User interface • Hardware • Software • Communication | N/A |  | Analysis
|  |  | Bảo mật | UC-005 | UC-005 NAME | Public User | Functional Requirement | A single statement of one individual function. Sometimes referred to as TSS statements: “The system shall …” Functional requirements and other types of requirements information typically are embedded in the software requirements specification (SRS) document.
|  |  |  | UC-006 | UC-006 NAME | Admin User | Quality Attribute | A quality characteristic that the system should possess. Sometimes referred to as quality factors or quality of service requirements. Examples: • Performance • Reliability • Scalability • Security • Redundancy • Backup requirements • Usability • Availability
|  |  |  | UC-007 | UC-007 NAME | Public User or Admin User | Solution Idea | A solution and/or statement of design. Usually stated by a business stakeholder, development or implementaton team member, or even by the BA during project initiation or analysis. Examples: • “We’ll need a new server for this application refresh.” • “The public will have to book reservations only through the online system.” It’s usually best to work backwards from a solution idea to identify the underlying business requirement: “What problem are we trying to solve?”
|  |  |  | UC-008 | UC-008 NAME | Public User | Use Case or Usage Scenario | Describes a process (collection of individual steps). Examples (possible use case name is underlined): • “Users will be able to post payments to customer accounts.” • “Users will be able to run accounts receivable agings reports.” If starting from a use case or usage scenario requirement, it can be used as a way to identify functional requirements. Its name should always start with an action verb.
|  |  |  | UC-009 | UC-009 NAME | Admin User | Configuration
|  |  |  | UC-010 | UC-010 NAME | Public User or Admin User
Note on R1: Implementation Priorities on Requirements worksheet. 1: Must Have 2: Should Have 3: Nice to Have 99: Dropped From Project (Inactivated)
Note on T1: Testability Methods on Requirements worksheet. Modify as needed.